## Sheet1
Relocate Deficient Maintenance Facility from Stehekin River Flood Plain to Comply with GMP
North Cascades National Park
PMIS: 195864A
2014-02-24
Estimate is based on 2014 costs
Item No. | Description | Site | Maintenance Facility | Maintenance Storage | Solid Waste
F20 | Demolition of Existing Facilities
| Remove Maintenance, Storage and Fuel Facilities | 100485
| Remove Wood Shop | 30000
G10 | Clear Site, Large Trees | 150420
G20 | Chip Seal, 2 coat | 70000
| Fencing | 5000
| Signage/site specialties | 5000
| Landscaping, minimal | 20000
G30 | Site Civil/Mechanical Utilities
| Water Line | 99683
| Electrical Line | 110217
| Phone/Data | 112450
| Propane System | 50000
| Septic System | 80000
| Water Storage - 180,000 gallon | 140000
| Emergency Generator with tank | 50000
| Site Lighting | 20000
A10 | Foundations, Excavation and Backfill |  | 8189 | 2906 | 3739
| Concrete Spread Footings, Reinforced |  | 33140 | 14310.9 | 17124
| Concrete Foundation Walls with Insulation |  | 25840 | 11356 | 19467
A20 | Basement, Concrete Slab on Grade, Reinforced |  | 30649 | 11979.9 | 15460
B10 | Superstructure, Column/Roof Structure and Decking |  | 98090 | 39007.8 | 50500
B20 | Exterior Stud Wall, Sheathing, Insulation and Veneer |  | 90305 | 37775.7 | 50890
| Exterior Door, Frame and Hardware |  | 18818.1 | 7467.5 | 8961
| Exterior Overhead Door and Frame |  | 15064 | 7532 | 15064
| Exterior Window and Wood Clad Frame |  | 10000 | 7000 | 10000
B30 | Roofing, Rigid Insulation and Flashing |  | 70684 | 28003 | 32445
C10 | Interior Stud Wall and Gypsum Board |  | 45500 | 33616.5 | 23690
| Interior Door, Frame and Hardware |  | 54075 | 20342.5 | 21630
| Interior Window and Frame |  | 24205 | 18309 | 11134
| Base and Upper Cabinets |  | 10574 | 7625.7 | 9682
| Building Specialties |  | 13451 | 5321 | 6180
C20 | Interior, Floor, Wall and Ceiling Finishes |  | 25869 | 8868.5 | 8240
D20 | Fire Sprinkler System |  | 15714 | 6216.5 | 7220
| Plumbing Fixtures and Piping |  | 85803 | 15377 | 54590
D30 | HVAC System |  | 80541 | 20057.5 | 50680
D50 | Electrical System |  | 103123 | 20831 | 47380
G10 | Finish Grade Site |  | 11323 | 4478.5 | 5200
G20 | Site Improvements
| Concrete Apron |  | 13296 | 12673 | 10429
Helipad with Fuel Tank
| Hazmat Storage Building |  |  | 169435
| Vehicle Canopy/Structure |  | 29200 |  | 30000
| Chainlink Fence with Gates |  |  |  | 18025
| Fuel Facility |  |  |  | 23175
Covered Storage, Solid Waste, Option
| Subtotal Direct Construction Costs | 1043255 | 913453.1 | 510490.5 | 550905
Published Location Factor (-7 Percent)
| Location Factor (2.5 Percent) | 26081.375 | 22836.3275 | 12762.2625 | 13772.625
| Remoteness Factor (40 Percent) | 417302 | 365381.24 | 204196.2 | 220362
| Federal Wage Rate Factor (7.5 Percent) | 22198 | 32075.97 | 15198 | 12420.92
| Washington State Tax (8.4 Percent) | 36906 | 43887.6296 | 20906 | 18627.1456
| Design Contingency (15 Percent) | 156488.25 | 137017.965 | 76573.575 | 82635.75
| Sustainability (0 Percent) | 0 | 0 | 0 | 0
| Total Direct Construction Costs | 1702230.625 | 1514652.2321 | 840126.5375 | 898723.4406
| Standard General Conditions (10 Percent) | 170223.0625 | 176995.2025 | 111852.7 | 107164.6366
| Government General Conditions (6 Percent) | 102133.8375 | 106197.1215 | 67111.62 | 64298.7819
| Historic Preservation Factor (0 Percent) | 0 | 0 | 0 | 0
| Subtotal NET Construction Cost | 1974587.525 | 1797844.556 | 1019090.8575 | 1070186.8591
| Overhead (15 Percent) | 296188.1287 | 307971.6523 | 307971.6523 | 307971.6523
| Profit (10 Percent) | 197458.7525 | 205314.4349 | 205314.4349 | 205314.4349
| Estimated NET Construction Cost | 2468234.4062 | 2311130.6432 | 1532376.9446 | 1583472.9462
| Contracting Method Adjustment (Competitive Negotiation: 5%) | 123411.7203 | 128321.5218 | 81065.5 | 77694.3615
| Bond and Insurance (2.0 Percent) | 49364.6881 | 51328.6087 | 32437.3 | 31077.7446
| Total FY2014 Estimated NET Cost of Construction | 2641010.8147 | 2490780.7737 | 1645879.7446 | 1692245.0523
Inflation Escalation - 0: Keep in FY2014
| Total Escalated Estimated NET Cost of Construction | 2641010.8147 | 2490780.7737 | 1645879.7446 | 1692245.0523
| Total Net Cost of Construction for Maintenance/Storage/Solid Waste |  | 8469916.3853
| Construction Contingency (10%) | 264101.0815 | 249078.0774 | 164587.9745 | 169224.5052
| Construction Management (8%) | 211280.8652 | 199262.4619 | 131670.3796 | 135379.6042
| Gross Cost of Construction | 3116392.7613 | 2939121.3129 | 1942138.0987 | 1996849.1618
| Gross Cost of Construction for Maintenance/Storage/Solid Waste |  | 9994501.3347